## Sheet1
Sr. no. | Projects/Activites | Project Code | People involved in the project | Pointers | Responsibilities | Target Date | Status
1 | POC for BEZA & POC for Environmental Monitoring | BGISSM - 008 | Pranav, Shailendra | Will be shown to Milan and Deepak | Pranav and Shailendra | 2023-04-08
2 | Document Control Activity |  |  | Alam Sir and Deepak Sir will give demo on Filing System to be followed on the server | Deepak and Alam | 04/08/2023 - 11am
3 | NBR | BGISCP - 007 | Sanket, Akash Nade, Prateek and Navnath | a) Finish PDF of Help Document | Sanket | 17/08/2023
|  |  |  | b) Functional Document to be prepared | Sanket (+ Akash & Prateek ) | 17/08/2023
|  |  |  | c) Small changes are being tested and made | Navnath
4 | GRAM-AWAS | BGISSM - 007 | Sanket & Akash Nade | a) Sanket to send email to Abhichand informing him that he'll be ready with the changes on the requested GRAM-AWAS module | Sanket | Internal Submission - 11/08/2023 Meeting - 14/08/2023
5 | MMRDA | BGISCP - 005 | Akash Nagi, Jafar Khan, Sumit | a) All 4 modules testing will be finished | Akash Nagi, Jafar and Sumit | 2023-07-08
|  |  |  | b) Meeting and Testing with Deepak | Akash Nagi, Jafar, Sumit and Deepak | 2023-09-08
6 | Krishi GRAM |  | Amol Bhore, Jafar Khan, Nishant Bodke | a) Tasks remaining - Weather Sensor Data (Backend) & Layer Publishing (Frontend) (**Project is on hold since exact weather data has to be collected and integrated from Prof. Lanka)
|  |  |  | b) Functional Documentation will be shown to Deepak and Milan | Nishant Bodke | 18/08/2023
7 | G-RAM GIS (Nashik) | BGISSM - 011 | Manesh, Akash Nagi, Abhay Sir, Prateek, Sumit, Arman, and Jafar | a) Prateek has to give Measurement, Editing & Draw Tools | Prateek | 2023-04-08
|  |  |  | b) Akash Nagi will solve the bugs | Akash Nagi | 2023-10-08
|  |  |  | c) GPR data is 90% wrong. Deepak & Kapilesh will finalize new vendor who will start this work by September. Deepak will give Sccope of Work of GPR today to Kapilesh. Kapilesh will call the following companies: - Garuda Survey - IG Drones - PDC Kapilesh will do research to find more GPR companies | Kapilesh and Deepak
|  |  |  | d) Milan & Deepak to have phone call with Abhay tomorrow to get data from him | Milan and Deepak | 2023-04-08
8 | Aarogya Aaplya Daari |  | Deepak - Project Director/Technical Lead Anushka - Project Manager Jafar - Backend Akash Nade - Backend Arman - Backend Abhishek - Mobile Dev Nishant - Frontend | a) Anushka will finalize the project schedule & linkages based on the WBS Activities by EOD Tomorrow. Prepare Charts. | Anushka | 2023-04-08
|  |  |  | b) Scope of Work | Anushka | 2023-07-08
|  |  |  | c) Financial Budget | Anushka and Deepak | 2023-07-08
(Our understanding is that the Smile Foundation will give us the money)
(Deepak says that we have to finish this project by 15th August anyhow, as per AMC's confirmation)
|  |  |  | d) First Draft ready | Entire team | 15/08/2023
9 | TreeLov | BGISCP - 003 | Abhishek, Arman, Navnath | a) Algorithm along with initial demo of monitoring tree growth through satellite imagery will be done in two months |  | 2023-03-10
|  |  |  | b) Deepak will give 1 pricing model for obtaining & analysing data sets of Google, Satellite, and Hyperspectrum which will be presented to Minority | Deepak | 2023-12-08
|  |  |  | c) TreeLov app interface - Navnath will review and by tomorrow evening give estimate of time required for testing | Navnath
10 | Claim Assure | BGISCP - 010 |  | Project on Hold
11 | LIDCOM |  |  | Kapilesh and Deepak have to win the project for us | Deepak and Kapilesh
12 | Skatec - 1 | BGISSM - 015 |  | Completed
| Skatec - 2 (LIDAR) | BGISSM - 017 |  | By 7th of September, Kapilesh to ensure getting drone permission | Kapilesh
Legend:
1) Cells shaded in green are footnotes